## PSP1 Project Plan Summary form
/Proyecto/PSP1
PSP1 Project Plan Summary
Project Settings
Project Owner | Daniel Melgarejo
Start Date | feb 19, 2017 12:00:00 AM
Completion Date | feb 21, 2017 10:55:50 PM |  |  |  | Completed: *
Keywords | Contador Lineas
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 167 | 72.3 | 72.3
Program Size
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 500 | 358 | 358
Reused (R) | 10 | 5 | 5
Added and Modified (A+M) | 500 | 358 | 358
Total Size (T) | 510 | 363 | 363
Total New Reusable | 0 | 348 | 348
Estimated Proxy Size (E) | 358 | 348 | 348
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.0083333 | 0.029861 | 0.029861 | 14.5%
DiseÃ±o | 0.041667 | 0.029167 | 0.029167 | 14.1%
CodificaciÃ³n | 0.041667 | 0.11875 | 0.11875 | 57.6%
CompilaciÃ³n | 0.0041667 | 0.0034722 | 0.0034722 | 1.68%
Pruebas | 0.020833 | 0.0076389 | 0.0076389 | 3.7%
Postmortem | 0.0083333 | 0.017361 | 0.017361 | 8.42%
Total | 0.125 | 0.20625 | 0.20625
Defects Injected
| Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0%
DiseÃ±o | 1 | 1 | 25%
CodificaciÃ³n | 3 | 3 | 75%
CompilaciÃ³n | 0 | 0 | 0%
Pruebas | 0 | 0 | 0%
Total | 4 | 4
Defects Removed
| Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0%
CodificaciÃ³n | 3 | 3 | 75%
CompilaciÃ³n | 0 | 0 | 0%
Pruebas | 1 | 1 | 25%
Total | 4 | 4
After Development | 2 | 2
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:57 PM el 21/02/2017